Insert current date

Dear DNR Regional Forester:

You are receiving this letter because an EAB infestation has been confirmed in your management area. The Emerald Ash Borer was detected in location, WI on date. Work to obtain more information on this detection and how to manage the EAB is beginning now. Within the next 10 business days you will need to assign a staff person to work on these new EAB related activities and report their contact information to the EAB Operations Group.

During the summer of 2009 The State of Wisconsin Cooperative Emerald Ash Borer Program developed tools to guide local response activities for Emerald Ash Borer detections and subsequent infestations.  Attached is the most recent update.  The need for specific guidance coupled with the need for local participation to meet increased workloads and other considerations not initially dealt with in the Wisconsin EAB Response Plan prompted the development of these tools.

Enclosed with this letter you will find a packet containing information explaining the roles and responsibilities of local, State and Federal staff in response to a new EAB detection and infestation site. The packet contains a diagram outlining the Wisconsin EAB ICS (Incident Command System) Response Structure, a list of EAB Response Unit resource documents and a list of local EAB contacts. These references will provide you with an overall picture of what to expect now that the EAB is in your area.

State and local agency personnel in your area will be charged with forming an EAB Response Unit. This unit will work closely with the EAB Operations Group to insure a safe, efficient and timely response to Emerald Ash Borer in this region. The EAB Operations Group will assist with initial set-up, and will provide sustaining guidance throughout the duration of EAB work in the Oak Creek area.

The Wisconsin EAB Operations Group will contact you to begin the set-up process. Please contact Jeff Weatherly at 414-263-8611 with immediate concerns. Thank you for your willing participation. We look forward to working with staff in your area to mitigate the impacts of the EAB on our valuable ash resource.

Regards,

The EAB Operations Group

JoAnn Cruse-APHIS, Bob Dahl-DATCP, Andrea Diss-Torrance-DNR, Brian Kuhn-DATCP, Barb Larson–UW Extension, Eric Oliphant – BIA, Dick Rideout-DNR, Mark Theisen-USFS, , Art Wagner-APHIS, Jeff Weatherly–DNR

Cc: DNR Urban Forester

Emerald Ash Borer

Multi-Site Response Guide

January 22, 2011

Summary

The Emerald Ash Borer (EAB) was detected for the first time in Wisconsin in 2008. In 2009 EAB was detected again, in four distinctly separate locations in the State. The EAB Response Plan drafted and approved by the Wisconsin Emerald Ash Borer Cooperative Program in July 2008 initially called for the use of a detailed Incident Command Structure to respond to EAB detections. The original State EAB response strategy was utilized to guide operations during the 2008 Newburg EAB detection; however the recent EAB detections and their unique nuances led agency staff to consider alternative approaches to working in and with multiple EAB affected areas simultaneously.

In order to appropriately and efficiently utilize available resources, the EAB Operations Group developed an amended strategy for working with new EAB detections and infestations. Representatives from all cooperating agencies provided input and the plan was approved by the State EAB Advisory Group.

The changes incorporated into the EAB Response Plan allow for strong leadership and decision making at the local level (in the area of impact) as well as flexibility to incorporate newly evolved science-based initiatives in the areas of survey, regulation and management.

The new response strategy will look at EAB detections and infestations on a case by case basis. Response to EAB detections will now involve the EAB Operations Group working with a multi-agency team of locally-based staff. The local team will be identified as a Response Unit.  These response units will be developed as needed to appropriately manage all EAB related tasks in a given area. The area a Response Unit manages could be as small as one municipality or it could be large enough to cover several counties. Each local unit will have a staff member(s) uniquely suited to handle the following tasks: EAB survey, regulatory measures, outreach & education and resource management.

The coalition created between the EAB Operations Group and the various Response Units will be able to merge central office resources with local resources to make beneficial decisions and carry out assignments in a timely, efficient and effective manner.

Complete information on this revision to the State’s EAB Response Strategy may be found at www.emeraldashborer.wi.gov.

The EAB Operations Group

JoAnn Cruse-APHIS, Bob Dahl-DATCP, Andrea Diss-Torrance-DNR, Brian Kuhn-DATCP, Barb Larson–UW Extension, Eric Oliphant – BIA, Dick Rideout-DNR, Mark Theisen-USFS, , Art Wagner-APHIS, Jeff Weatherly–DNR

EAB Multi-Site Infestation Response Guide

January 9, 2011

In the future we can expect to find more populations of EAB around the state.  Handling several populations concurrently requires that we streamline the response state agencies provide each infestation.  The Operations Group made the following modifications to the Response Plan in order to better handle multiple populations and be sustainable with the current staff and resources of participating agencies.  The Response Unit is meant to meet short term needs (about one year) and segue to long term management handled as part of the regular workload of staff.

Response Unit Coordination

While Response Units will function semi-independently, there will be a need for statewide coordination to assure state goals are addressed in the course of responding to individual or groups of infestations.  Statewide coordination can also allow for sharing of labor intensive services such as workshops so that one serves the needs of several units.  This coordination will be done by the EAB Operations Group.  The Operations Group will assess the statewide situation and request infestations be handled individually or in groups as appropriate.  The Operations Group will also provide guidance on the range of options for actions appropriate to specific infestations given state goals and staff availability.  Communication between Response Units and the Operations Group is through a liaison member of the Operations Group, usually the one representing field forestry. Generally, Response Units would not plan actions that would require more staffing than they have available at their local level.  Projects requiring a large number of staff, such as a Slow Ash Mortality (SLAM) approach to an infestation or the declaration of a zone of infestation, would only be undertaken at the direction of the Operations Group which would arrange for sufficient resources and staffing to accomplish the larger project.

Response Unit Formation

Once a new EAB population location has been confirmed the following will occur:

- Partner notification by state agencies

- Community notification by state agencies

- The Operations Group will convene to request the formation or an expansion of an EAB Response Unit

- The Operations group will contact DNR Regional Forestry Supervisors and communicate their final decision.

These four steps will occur in a matter of days following EAB detection.

Response Units must fulfill planning for the following functions in the first year following a find; Survey, Regulation, Outreach and Education, and Management.  Some of these functions will be the responsibility of one state agency; some will involve staff from two or more agencies.  Response Units will be locally focused with staff from the area filling crucial positions.  That being said, functions may be filled by state or municipal staff at the state, regional or local level as appropriate for the task or the area of responsibility of a unit handling planning for more than one infestation.  The lead for the unit should be a DNR staff person handling management as he or she is most likely to be located nearest the infestation and be most aware of local needs.  The lead will be the point of contact with the Operations Group liaison.

Response Unit Goals and Corresponding Timeline of Goal Achievement

Once established, each Response Unit must develop a document outlining goals for their particular work group.  Response Units should plan their activities to occur within approximately 10 miles of the EAB detection, though this area of responsibility may expand at the request of the Response Unit.  This may be appropriate for some projects in some situations.  For example, a public education campaign for a find in a rural area with a sparsely distributed populace.  The plan should include a one-year timeline for EAB work activities and must include the following functions:

- Survey: Include initial survey plans, type of survey work scheduled and when it will be completed.  This section can be a checklist if it is similar to options included in EAB Survey Details in Appendix B.

- Regulation: Include set up and establishment of quarantine zone (if needed), procedures and timelines for back tracing and forward tracing if requested by the Operations Group, and estimate of compliance agreements needed in area.  This section can be a checklist if it is similar to options included in EAB Regulatory Details in Appendix B.

- Outreach & Education: Determine what levels of outreach are needed and a timeline for when they will take place. Include information on public meetings, where and how many educational brochures will be distributed and media interviews/contacts.

- Management: Timeline for initial management activities and what types of long term activities will be handed off to local staff for implementation.

Response Units can select among the bulleted functions described below for appropriate actions for their situation or propose new approaches to achieve these goals.  A checklist of recommended and potential activities is provided in Appendix C to help in the development of your plan.  The plan itself should be in a narrative format which could include a checklist for activities that are routine for a response to an EAB find and need no further explanation.  Detailed descriptions of activities should be limited to those which are not generally practiced or are unique to this specific response: activities that would need some explanation for a reader.

Once completed, the plan is sent to the Operations Group liaison for review within two weeks.  If the liaison has concerns about any of the proposed projects, he or she will refer his or her concerns to the Operations Group.  The Operations Group would have two additional weeks to consider the project in question and provide approval or feedback for improvement.  During the review process, the Response Unit can move forward on all non-controversial projects.  The Operations Group will coordinate any projects that require cooperation between units and provide support needed by the Response Unit to achieve its goals. The Response Unit will also notify local partners once the group is formed and work is beginning.

Response Unit Closeout Process

Response Units should plan to address only those needs that must be met within about one year of the discovery of the EAB population in the area for which they are responsible.  Longer term projects should be handled as part of the normal pest management workload.

Response Units will start out with members who are responsible for each of the four functions.  Once the planned projects addressing a function are done and a final report for that function completed, the member responsible for that function may leave the Unit unless their expertise is need for projects of another function.

Once the goals for a unit have been met, the remaining member(s) should assemble the final report from those submitted from each functions member.  The report is sent to the Operations Group liaison after which the unit may disband.

Response Unit Functions

Survey

Survey is done around a find if it appears to be distinct from previously known populations and/or if this information is needed to implement regulatory or management activities.  There is a range of survey intensities and each distinct find will be assessed by the Operations Group as to what level of survey intensity is initially appropriate, if any, with input from the local Response Unit on what information they need to do the regulation and management work planned.  In nearly all situations, a newly found population will clearly fall into one of two categories: 1) new detections in isolated areas, or 2) detections in known infested areas and quarantined counties.  The following survey activities are appropriate for each category.  Response Units select among the survey options for the type of infestation for which they are responsible or may choose to do no survey if that is most appropriate to the situation.  For details of all of these survey options, see Appendix B.

EAB surveys and tools applicable to new detections in isolated areas:

- Rapid visual survey

- Aging of infestation

- Delimitation survey

- Aerial and/or satellite survey

EAB surveys and tools applicable to detections in known infested areas and quarantined counties:

- Rapid visual survey

  - to monitor changes in an area of infestation

  - resource dependent

- Aerial and/or satellite survey

If survey is necessary, the DATCP staff person who will coordinate the survey for a particular Response Unit will be designated by DATCP supervisory staff. DATCP will lead survey initiatives but may require the assistance of local personnel resources to carry out survey operations in a given area.  For example, DNR or municipal foresters may be asked to conduct visual surveys of specific areas.

Regulation

Regulation includes both the placement of quarantines or zones of infestation where they did not already exist as well as actions that follow.  Bob Dahl (DATCP) is the lead person on regulatory issues of woody plants for the State.  For each Response Unit, Bob will designate the DATCP regulatory staff person who will cover this function for the unit.  For details of all of these regulatory options, see Appendix B.

EAB regulatory activities corresponding to new detections in isolated areas:

- Inform all known parties (such as arborist, mulch producers, timber mills, firewood dealers, pallet producers, timber buyers, and cooperating foresters) in writing of quarantine regulations.

- Seek additional parties that need to be informed of the quarantine.

- Work with DNR / Forestry staff as appropriate.

- Conduct compliance checks

- Administer Compliance Agreements

- Forward or Back Tracing as requested by Operations Group

EAB regulatory activities corresponding to known infested areas and quarantined counties

- Conduct compliance checks

- Administer Compliance Agreements

Outreach and Education

Effective containment and management of EAB requires the participation of the public.  Outreach and education thus play a crucial role in reducing the spread of EAB and managing its impacts.  Response Units should focus on the outreach and educational needs specific to immediate (within the first year) regulatory and management needs of the infestation or infestations for which it is responsible.

Localized area of EAB population:  UW Extension will be active in serving local needs for awareness of EAB infestations and what people in the area need to do to respond to the population of the pest.  Outreach efforts could include,

- Organizing workshops for local governments, landowners, and the general public on what has been found and options for responding to the local threat.  The EAB Operations Group will help coordinate Response Units so workshops can benefit two or more infested areas if practical.

- Help make key community leaders, citizens, business, landowners, and others more aware of regulatory requirements surrounding issues like quarantines and firewood movement.

- Providing educational material to local businesses and gathering places on how the public can prevent spreading EAB in firewood.

- Serving as a local media contact.

- Making local residents and governments aware of outreach and educational resources available to them.

- Working with local government staff to disperse educational messages.

- Serving as a communications link between local government and DATCP and DNR staff.

- Making personal contacts with businesses and community leaders, especially in rural communities.

Targeted Audiences:  DNR and UW Extension staff will carry messages to targeted audiences.  Targeted outreach efforts include,

- Providing technical advice for management of EAB to communities and woodland owners in the area of infestation.

- Providing training on preventing spread of EAB to private foresters, loggers, ROW clearing crews, arborists and other industry professionals.  Contact information for specific groups in the infested area may be available from DATCP regulatory staff.

- Presentations to woodland owners and affected community residents on management options.

- Providing workshops on specific topics such as utilization of infested wood.

Management

Guiding management of EAB will primarily be the responsibility of DNR and municipal foresters of affected areas.  Response Units plan and implement projects that meet immediate (within the first year), local management needs for the infestation or infestations they serve.  Longer term management should be considered part of the normal pest management workload of the local foresters, both DNR and municipal. Training staff, inventorying local resources or other preparatory work for local staff taking on the responsibility of managing EAB in their area, however, would be appropriate projects for the Response Unit.  In developing the plan, separate tasks that are similar to normal work for a forester or urban forester from projects that are unique to the area for which the unit is responsible.  Common tasks to help communities and landowners manage the EAB and their ash resource need only a short description and are primarily listed so that the Response Unit staff can track them and check them off when completed.  Unique projects should have more description so that future unit staff may recognize and use unusual approaches for uncommon situations.  For example, assisting communities develop an ash management plan would be listed among those tasks similar to normal urban forester work.  In contrast, developing an ash management plan to prevent flooding due to downed, dead ash along river- ways in the community is unique and should be presented in more detail.

Whether local, regional or state staff would be assigned to a Response Unit will depend on whether one or several infestations are served by a unit or the local needs for expertise, (rural or urban for example). DNR regional directors should favor assigning the most local staff person given the area of the Response Unit’s responsibilities.  Potential projects include,

- Developing local EAB forest management response objectives.

- Providing local woodland owners with sustainable forest management recommendations aimed at mitigating EAB impacts.

- Facilitating forestry management practices such as group salvage/sanitation timber sales for small landowners.

- Assisting forest tax law landowners with modifications of forest management plans.

- Advising communities on tree removal, processing and reforestation.

- Advising communities on management options, including treatments.  County and community foresters would be involved in setting and accomplishing immediate goals at these government levels.

- Conducting or guiding forest or urban ash tree inventories.

- Facilitating utilization of the ash resource by connecting woodland owners and communities with forest products markets.

- Working with federal agencies and universities to test new management techniques or utilization options.

- Assisting in the release or monitoring of beneficial organisms.

- Offering grant opportunities to affected communities and landowners.

Appendix A: EAB Response Unit Resources

January 22, 2011

All of the following resources can be found online at the Wisconsin Cooperative Emerald Ash Borer Resource Website at http://emeraldashborer.wi.gov.  Look on that website for the buttons (left menu bar of website) and tabs (top menu bar) mentioned below to find links to download these documents.

Survey

- Current DATCP EAB Survey Program Information is available from the Survey Program button on the WI EAB website.

Regulations

At the For Communities button and at the For Woodlot Owners button:

- Managing Emerald Ash Borer (EAB) Infested Wood ~ Regulations and Recommendations for Transport, Storage, Utilization and Disposal.

At the State and Federal Quarantines button:

- Commercial Transportation of Ash Wood for Utilization or Disposal

At the For Homeowners button:

- Ash Wood Processing Options for the Homeowner

At the Resources tab and at the State and Federal Quarantines button:

- Easy Guide for Emerald Ash Borer Regulations

Management

Wisconsin Emerald Ash Borer Response Activities and Program Strategies for the most current year are available at the Wisconsin’s Response Plan button, including but not limited to:

- Wisconsin Cooperative EAB Response Plan

- Wisconsin EAB Multi-Site Response Plan

At the Resources tab:

- Wisconsin EAB Management Guidelines

- Urban Ash Management Guidelines

At the For Communities button:

- EAB Toolkit

At the For Woodlot Owners button:

- Emerald Ash Borer and Forest Management – Silvicultural Guidelines

Outreach & Education

The following are available via the listed DNR forestry publication #s at the DNR warehouse:

- Posters are available for download from the Resources tab at the top menu bar on the WI EAB website include 8.5 x 11 and 8.5 x 14 versions of firewood quarantine posters for public (DNR) and private properties, EAB look-alike posters and much more.

- The Green Menace tri-fold brochure by USDA (Pub# FR-348)

- EAB Field Guide – signs of infestation plastic card (Pub# FR-458)

- EAB Field Guide – ash tree and EAB ID plastic card (Pub# FR-459)

- And the Wisconsin Cooperative Emerald Ash Borer Resource Website: www.emeraldashborer.wi.gov

Appendix B: Details of EAB Survey and Regulation Options

EAB Survey Options for Response Units

- Delimitation Survey

  - The decision of whether to do a delimitation survey and or aging an infestation will be made by the Operations Group with input from the Response Unit for that infestation.

  - This type of survey is most appropriate where a find appears completely distinct from known populations and in a situation that would require the placement of quarantine or other regulatory action.  For example, where a new county would be quarantined or where a new zone of infestation would need to be declared within a quarantined area.

  - This type of survey is the most intensive.  It involves prism traps in a gridded area or visual surveying combined with cutting and peeling suspect trees if the survey must be done outside the summer flight period.

  - Delimitation surveys are considered completed after one season or one year if multiple techniques are determined to be necessary by the Operations Group.

  - DATCP staff will generally conduct delimitation surveys with assistance of municipal and/or local DNR staff facilitating access to sites and trees for cutting and peeling or with the survey itself.

- Aging of the Infestation

  - Aging of the infestation using tree cores or “cookies” would normally only be done as part of a delimitation survey.  Not all delimitation surveys may require aging of the population.

  - A method to estimate infestation age from condition of ash may eventually be developed.  This coarse estimation technique could be used in rapid visual surveys.

- Rapid Visual Assessment (RVA)

  - This technique is the least intensive and quickest but least sensitive method of surveying for signs and symptoms of EAB infestation.

  - RVA could be done on request by Response Units, communities or agencies if the information is needed and would be sufficient for specific management purposes.  Requests for an RVA would go through a Response Unit to the Operations Group for decision.

  - DATCP staff would lead most RVA with local and/or municipal staff playing a significant role.

- Aerial or satellite surveys of discoloration, dieback and mortality

  - These surveys are not specific to damage done by EAB and ground-truthing is required to confirm EAB tree mortality.

  - Aerial surveys are done as part of normal work by DNR forest health staff where there is significant, map-able mortality.

  - Satellite surveys may be used more in the future as a tool to detect distress in trees.

EAB Regulation Options for Response Units

- Development of contact lists for specific regulated groups

  - Groups would include firewood dealers, portable sawmill owners, tub grinder operators and others.

  - These lists would be used in regulation, outreach and education and management efforts.

  - DATCP staff will develop contact lists with assistance from local municipal and DNR staff.

- Compliance Agreement Administration and Compliance Checks

  - This will be an on-going workload as regulated businesses start or expand into the quarantined area.

  - DATCP and APHIS staff handle compliance agreement development and administration.  Members of any agency should report incidences of non-compliance to DATCP staff.

- Back Tracing

  - In many cases, the infestation will be obviously too old to determine how it was initially brought into the area.  The Operations Group will determine if back tracing will be attempted for a new infestation.

  - If done, and depending on the circumstance, DATCP or APHIS staff would do back tracing.

- Forward Tracing

  - Since forward tracing can be done on recent movement of material, they can be done in almost all situations but may not be necessary for all infestations.

  - Forward traces done immediately after identification of an infestation may be helpful in determining needed compliance actions or in targeting education efforts.

  - Depending on the circumstance, DATCP or APHIS staff will do forward tracing.

Appendix C: Checklist of Recommended and Potential Activities for EAB Response Units.

This checklist is provided as a tool to help Response Units sketch out their plan. The final plan should be in narrative format though it may contain checklists or tables.  Activities highlighted in pink are strongly recommended.

| WISCONSIN EAB OPERATIONS - RESPONSE UNIT CHECKLIST FOR WORK PLANNING |
| --- |
| Response Unit Name: (usually the location of the infestation) | Survey Member: Enter Name Here Enter Org Here | Regulatory Member: Enter Name Here Enter Org Here | Outreach/Education Member: Enter Name Here Enter Org Here | Management Member: Enter Name Here Enter Org | Date Plan Prepared |
| Additional Participating Members: (Name, Organization) | Anticipated Completion Date for Plan Activities : |
| Infestation Location – map attached Enter Location Here |
| Landscape Description and Narrative Urban Suburban Rural Enter Narrative Here |
| Immediate Local Response: completed within 2 weeks of formation of the Unit |
| Activity | Target Start Date | Target Completion Date | Lead Member of Unit | Comments & Explanatory Notes Pink highlighted items are strongly recommended |
| Assessment 1st rapid visual assessment | w/in 2 weeks of unit formation | Enter Date |  | Refine delimitation perimeter |
| Initial Public Alert | w/in 2 weeks of unit formation | Enter Date |  | post alert at public locations notification of local industry, communities of any immediate regulatory requirements meet with community leaders to explain situation if needed |
| Determine if affected community(s) has an EAB response plan |  |  |  | If community plan is available, get a copy and incorporate it into the infestation Response Plan. If community has no plan, encourage and assist rapid development of a plan, see Management section as this will take longer than the 2 weeks immediate response period |
| Survey Goal: Delimit and monitor the general extent and location of the EAB infestation. |
| Activity | Target Start Date | Target Completion Date | Lead Member of Unit | Comments & Explanatory Notes Pink highlighted items are strongly recommended |
| Determine survey needs for management activities planned by Unit |  |  |  | Note, it is not possible to request more prism traps be set at a location as that is determined by APHIS. |
| Communicate survey needs to the Operations Group |  |  | Response Unit Leader | Work with Ops Group to achieve appropriate survey strategies & tools for area |
| Survey |  |  |  | girdled detection trees, identify and establish 5 to 6 locations to further define the extent of the infestation. aging infestation winter visual survey cutting & peeling survey notification of communities of planned survey actions |
| Unit incorporates survey results and adjusts response activities accordingly |  |  |  | adjustmernt of planned activities should be done when new EAB distribution data becomes available |
| First Detector recruitment, training and management |  |  |  |  |
| Regulation Goal: Enforce EAB quarantine regulations through outreach, education, and regulatory action where necessary. |
| Activity | Target Start Date | Target Completion Date | Lead Member of Unit | Comments & Explanatory Notes Pink highlighted items are strongly recommended |
| Identify groups of special concern in the infestation area and give to DATCP regulatory staff |  | Enter Date |  | Examples: Amish community, tribal lands or non-tribal lands used by tribes for cultural purposes, absentee landowners |
| Firewood Certification Program Facilitate participation by firewood producers |  | Enter Date |  |  |
| Provide updates on regulatory activities in the infested area to the Unit |  |  |  |  |
| Signage Quarantine signs |  | Enter Date |  | Locate at county entrance/exits |
| Coordinate EAB compliant industries to aid planned management activities. |  |  |  |  |
| Outreach/Education Goal: Provide increased public awareness of EAB, regulations, and appropriate management. |
| Activity | Target Start Date | Target Completion Date | Lead Member of Unit | Comments & Explanatory Notes Pink highlighted items are strongly recommended |
| Identify education needs of local industry , populace and make plans to address them |  |  |  | Agencies will have contacts in different groups and will need to pool needs of all affected parties. |
| Identify any informational needs (research topics) and communicate to Ops Group |  |  |  | Agencies will have contacts in different groups and will need to pool needs of all affected parties. |
| Awareness Activities |  |  |  | Signage re quarantine borders & regulations located at borders of quarantined area Displays at local events, fairs, Arbor and Earth days Presentations to affected groups, WWOA, industry groups, local government, vacation home owners or camper conventions Outreach to tourists Outreach to public which use wood for heating and retail that serves the market. Outreach to ROW clearing companies and municipal crews |
| Education activities |  |  |  | Workshops and access to educational material on management tools for homeowners and communities including: pesticides, tree selection, diversification of residential forests, risk of moving and storing firewood. Field days training for loggers and ROW clearance crews w FISTA Demonstration events and permanent demonstration sites Training Master Gardeners and First Detectors if available in area. Communicate Best Management Practices to communities, industries, loggers, consulting foresters, arborists, ROW/ulitity clearance crews, and landowners Articles in local papers, newsletters, community access channels, radio shows. Options for utilization of cut trees. Training on forest management for landowners |
| Updates Every quarter year to Operations Group |  | Enter Date | Response Unit Leader | Report progress of response unit’s planned activities, emerging needs, additional relevant information that develops |
| Firewood Certification Program Encourage firewood producers to participate |  | Enter Date |  |  |
| Management – Serve Communities and Landowners Goal: Assist local landowners and communities with appropriate EAB management responses. |
| Activity | Target Start Date | Target Completion Date | Lead Member of Unit | Comments & Explanatory Notes Pink highlighted items are strongly recommended |
| Urge communities to identify location for secure storage and processing of infested wood |  |  |  |  |
| Facilitate multi landowner logging contract |  |  |  | May include doing inventory of included lands |
| Grant proposal to fund specific management activities or research |  | Enter Date |  | Submit through USFS |
| Communication of resources and grants available to communities and landowners for management activities |  | Enter Date |  |  |
| Encourage use of Urban Ash Management Guidelines for developing or updating community response plans |  | Enter Date |  | Especially encourage a multi pronged approach to management of EAB and the ash resource. |
| Assist Forest Tax Program participants in modification of existing plans |  | Enter Date |  |  |
| Develop partnerships RC&D wood utilization network |  | Enter Date |  |  |
| Provide Operations Group with resource needs for management |  | Enter Date |  | Provide to operations team |
| Ash Seed collection |  | Enter Date |  | Initiate seed collection from 3-5 unrelated mother trees per quarantined county for each native ash species (white, green, black), following WDNR Ash Seed Collection Project guidance. Fall |
| Develop local ash wood utilization lists |  | Enter Date |  | (e.g., mills with compliance agreements, local biomass markets, portable sawmill operators, etc.) |
| 5-mile management zone (1st priority – likely infested) |  | Enter Date |  | Begin conducting intensive EAB forestry operations to include: Create mailing list of all private forest landowners with 10 or more acres of forestland; contact landowners and provide them with EAB information and seek permission to do forest inventory work; conduct forest inventory to determine the amount, marketability, and distribution of the ash resource; provide sustainable stand-level forest management recommendations; facilitate/promote salvage and pre-salvage harvests of most or all ash following WDNR EAB silvicultural guidance for quarantined counties; identify potential “trap islands” or “lethal trap trees” that could be either incorporated with a harvest operation or completed through special funding if available; implement EAB management strategies on DNR lands |
| 5-15 mile management zone (2nd priority - likely infested within next 15 years) |  | Enter Date |  | Begin conducting EAB forestry operations to include: Facilitate/promote pre-salvage harvests of most or all ash( following WDNR EAB silvicultural guidance for quarantined counties; work with tax law landowners and other landowners who request service to update harvest plans and provide harvesting advice where ash is present; no trap islands are recommended in this zone. |
| 15+ mile management zone (3rd priority - high risk of infestation within next cutting cycle) |  | Enter Date |  | Continue normal sustainable forestry operations to include: accelerated harvest schedules in stands where there is a significant ash component; manage sustainably following WDNR EAB silvicultural guidance for non-quarantined counties. |
| Additional Activities |
| Activity | Target Start Date | Target Completion Date | Lead Member of Unit | Comments & Explanatory Notes |
|  |  | Enter Date |  |  |
|  |  | Enter Date |  |  |
|  |  | Enter Date |  |  |
|  |  | Enter Date |  |  |
|  |  | Enter Date |  |  |

__________________________________	_______________________

Plan Preparer				Date

_______________________________	_____________________

Reviewer				Date

_______________________________	_____________________

Approved				Date

# Text boxes

Appendix D: Example, Wisconsin EAB ICS Response Structure – January 2011

Community C

Community B

Community A

EAB Wood Utilization Committee

EAB Response Unit Ops Group Staff Liaison

EAB Operations Group

EAB Science Panel

EAB Communications & Outreach

Wisconsin EAB Advisory Group

Management Team Member

Outreach Team Member

Regulatory Team Member

Survey Team Member